## Sheet1
Master Thesis Timeplan |  |  | Start Date: | 2023-06-19 | 2023 | [27 empty] | 2024
[5 empty] | Juni |  | Juli |  |  |  |  | August |  |  |  | September |  |  |  | Oktober |  |  |  |  | November |  |  |  | Dezember |  |  |  | Januar
Task Group | Task | Progress | Start | Duration | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25 | 2024-01-01 | 2024-01-08 | 2024-01-15 | 2024-01-22 | 2024-01-29
Expose | Research on SH and SS | 100 | 2023-06-19 | 2
| Write the Expose | 95 | 2023-07-03 | 4
Research | Detailed understanding of the SH framework |  | 2023-08-07 | 1
| Understand different types of SS measures |  | 2023-08-14 | 1
| Detailed understanding of DL/NE-based SS |  | 2023-08-21 | 2
| Understand different NESS models |  | 2023-08-21 | 2
Conceptualization | Indentify software libraries to use for NESS |  | 2023-09-04 | 1
| Indentify most oportune integration point |  | 2023-09-11 | 2
| Indentify SH framwork modules to modify |  | 2023-09-11 | 2
| Identify modules that need to be added |  | 2023-09-11 | 2
Implementation | Add new modules to the SH framwork |  | 2023-09-25 | 3
| Permform necessary modifications of the SH framework |  | 2023-10-16 | 2
Evaluation | Obtain news header corpus used in previous evaluations |  | 2023-10-30 | 1
| Asses whether "CausalNewsCorpus" can also be used |  | 2023-10-30 | 1
| Design evaluation framework |  | 2023-11-06 | 1
| Run evaluations |  | 2023-11-13 | 6
Writing | Problem Statement |  | 2023-11-13 | 1
| Fundamentals and Related Work |  | 2023-11-20 | 2
| Solution Approach |  | 2023-12-04 | 2
| Implementation |  | 2023-12-18 | 1
| Results and Evaluation |  | 2024-01-01 | 1
| Introduction |  | 2024-01-08 | 1
| Conclusion |  | 2024-01-15 | 1
| Future Work |  | 2024-01-15 | 1
Correcting | Submit draft for feedback |  | 2024-01-22 | 2
| Incorporate feedback into final version |  | 2024-01-22 | 2